| Product Backlog Report Smart Energy Forecaster – CeDInt Storey 1 (TBDA, Group 1) Product: a data product that forecasts the normal hourly energy use of each zone (NE, NW, SE, SW) of CeDInt Storey 1, detects out-of-hours waste and abnormal consumption, and shows the € and CO₂ impact in a dashboard for the building manager. Backlog items are taken directly from our Jira project (KAN), grouped by the 8 epics and ordered by work-item number. Each item shows its Jira key, title and assignee; the whole team works on every sprint at the same time. Team: Amélie Buysse, Inge Haan, Emma Hendriks, Gabriele Grazzini, Hector Dessaux, Jo Elb, Linnéa Lindell, Marius Calves, Raffaele Simo, Simone Massucco, Viktor Kalinowski Status on 8 Oct 2026 · 77 items · 143 story points · 48 High, 26 Medium, 3 Low · Sprint 1 = Sep 28–Oct 11, 2 = Oct 12–25, 3 = Oct 26–Nov 8, 4 = Nov 9–22, 5 = Nov 30–Dec 14 | Status. Not Started. In Progress. Complete. Overdue. On Hold. |  | Priority. High. Medium. Low. |
| --- | --- | --- | --- |

| # | Jira key | Work item | Assignee | Priority | SP | Sprint | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Project management & Scrum · KAN-6 · Jira, repo, working agreements, risk register and Scrum events |  |  |  |  |  |  |  |
| 1.1 | KAN-8 | Jira project, backlog and sprints | Amélie Buysse | High | 1 | 1 | Complete |
| 1.2 | KAN-9 | GitHub repository and docs skeleton | Jo Elb | High | 2 | 1 | Complete |
| 1.3 | KAN-117 | Methodology choice and roles | Marius Calves | High | 2 | 1 | Not Started |
| 1.4 | KAN-116 | Working agreements: Definition of Ready, Definition of Done, communication plan | Inge Liv Haan | High | 1 | 1 | Not Started |
| 1.8 | KAN-130 | Risk register | Inge Liv Haan | Medium | 2 | 2 | Not Started |
| 1.9 | KAN-138 | Mid-project peer feedback | Inge Liv Haan | Medium | 1 | 3 | Not Started |
| – | KAN-28 | Scrum events and weekly sponsor update (every sprint, not story-pointed) | Inge Liv Haan | Medium | – | 1–5 | Complete |
| 2. Business case & value · KAN-112 · client problem, SDG/EELISA link and how success is measured |  |  |  |  |  |  |  |
| 2.1 | KAN-10 | Business question and definition of waste | Amélie Buysse | High | 2 | 1 | Not Started |
| 2.2 | KAN-120 | Stakeholders and personas | Hector Dessaux | Medium | 1 | 1 | Not Started |
| 2.3a | KAN-132 | Business case | Amélie Buysse | High | 3 | 2 | Not Started |
| 2.3b | KAN-136 | Business case updated with measured waste | Amélie Buysse | Medium | 1 | 3 | Not Started |
| 2.3c | KAN-153 | Final savings in the business case | Amélie Buysse | High | 1 | 4 | Not Started |
| 2.4 | KAN-131 | Success KPIs | Inge Liv Haan | High | 1 | 2 | Not Started |
| 3. Data foundation · KAN-4 · one clean hourly dataset with weather, calendar, prices and CO₂ |  |  |  |  |  |  |  |
| 3.1 | KAN-11 | Combine the 4 zone files | Simone Massucco | High | 2 | 1 | Not Started |
| 3.2 | KAN-12 | Data quality report | Raffaele Simo | High | 2 | 1 | Not Started |
| 3.3 | KAN-122 | Fix the timezone | Simone Massucco | High | 1 | 2 | Not Started |
| 3.4a | KAN-13 | Clean the data: counter resets and bad values | Simone Massucco | High | 2 | 2 | Not Started |
| 3.4b | KAN-123 | Clean hourly dataset | Raffaele Simo | High | 3 | 2 | Not Started |
| 3.5 | KAN-14 | Add outdoor weather | Marius Calves | High | 1 | 2 | Not Started |
| 3.6 | KAN-125 | Add holidays and academic calendar | Gabriele Grazzini | High | 2 | 2 | Not Started |
| 3.7 | KAN-134 | Add electricity prices and CO₂ | Simone Massucco | High | 2 | 3 | Not Started |
| 3.8 | KAN-129 | Data dictionary | Jo Elb | Medium | 1 | 2 | Not Started |
| 3.9 | KAN-160 | Repeatable data pipeline | Simone Massucco | Low | 2 | 5 | Not Started |
| 3.10 | KAN-149 | Publish results to the dashboard data layer | Simone Massucco | High | 1 | 4 | Not Started |
| 4. Exploration & waste definition · KAN-113 · what normal and wasteful use look like in Storey 1 |  |  |  |  |  |  |  |
| 4.1a | KAN-15 | Out-of-hours first look | Emma Hendriks | High | 2 | 1 | Not Started |
| 4.1b | KAN-127 | Out-of-hours use page | Linnéa Lindell | High | 3 | 2 | Not Started |
| 4.2 | KAN-16 | Standby baseline and empty-zone rule | Emma Hendriks | High | 3 | 2 | Not Started |
| 4.3 | KAN-124 | Temperature sensitivity | Marius Calves | Medium | 2 | 2 | Not Started |
| 4.4 | KAN-133 | Structural breaks and training window | Raffaele Simo | Medium | 1 | 3 | Not Started |
| 5. Forecast of normal consumption · KAN-5 · hourly expected use per zone, from naive baseline to final model |  |  |  |  |  |  |  |
| 5.1a | KAN-18 | Naive forecast (same hour last week) | Gabriele Grazzini | High | 2 | 1 | Not Started |
| 5.1b | KAN-126 | Weekday-hour median baseline on clean data | Gabriele Grazzini | High | 1 | 2 | Not Started |
| 5.2 | KAN-17 | Feature engineering | Marius Calves | High | 3 | 3 | Not Started |
| 5.3 | KAN-19 | LightGBM forecast per zone | Gabriele Grazzini | High | 3 | 3 | Not Started |
| 5.4 | KAN-146 | Prophet comparison | Gabriele Grazzini | Medium | 3 | 4 | Not Started |
| 5.5 | KAN-20 | Evaluation on time-based split | Raffaele Simo | High | 2 | 3 | Not Started |
| 5.6 | KAN-144 | Prediction interval | Marius Calves | High | 3 | 4 | Not Started |
| 5.7 | KAN-143 | Experiment log | Jo Elb | Medium | 1 | 3 | Not Started |
| 5.8 | KAN-162 | Final model and model card | Marius Calves | Medium | 2 | 5 | Not Started |
| 6. Waste & anomaly detection · KAN-114 · turning the gap between actual and expected into alerts with € and CO₂ |  |  |  |  |  |  |  |
| 6.1 | KAN-145 | Detect abnormal consumption | Emma Hendriks | High | 3 | 4 | Not Started |
| 6.2 | KAN-22 | Detect out-of-hours waste | Emma Hendriks | High | 3 | 3 | Not Started |
| 6.3 | KAN-23 | € and CO₂ per alert | Amélie Buysse | High | 2 | 3 | Not Started |
| 6.4 | KAN-152 | Severity levels | Amélie Buysse | High | 2 | 4 | Not Started |
| 6.5 | KAN-148 | Separate data errors from real waste | Simone Massucco | Medium | 2 | 4 | Not Started |
| 6.6a | KAN-137 | Catalogue of known events | Inge Liv Haan | Medium | 2 | 3 | Not Started |
| 6.6b | KAN-24 | Validate against known events | Raffaele Simo | Medium | 2 | 4 | Not Started |
| 6.7 | KAN-150 | Tune the alert threshold | Inge Liv Haan | Medium | 2 | 4 | Not Started |
| 6.8 | KAN-135 | One alert table for all detectors | Simone Massucco | High | 1 | 3 | Not Started |
| 6.9 | KAN-163 | Final alert review | Emma Hendriks | Medium | 2 | 5 | Not Started |
| 7. Dashboard · KAN-7 · what the building manager sees and uses every day |  |  |  |  |  |  |  |
| 7.1a | KAN-121 | Low-fidelity wireframe of all screens | Hector Dessaux | High | 1 | 1 | Not Started |
| 7.1b | KAN-21 | Mockup of all screens | Hector Dessaux | High | 3 | 2 | Not Started |
| 7.2 | KAN-118 | Dashboard stack and running skeleton | Viktor Kalinowski | High | 2 | 1 | Not Started |
| 7.3a | KAN-128 | Overview page v1 | Viktor Kalinowski | High | 2 | 2 | Not Started |
| 7.3b | KAN-156 | Overview page complete | Linnéa Lindell | High | 1 | 4 | Not Started |
| 7.4 | KAN-26 | Actual vs expected chart | Viktor Kalinowski | High | 3 | 3 | Not Started |
| 7.5 | KAN-157 | Floor map of Storey 1 | Hector Dessaux | Medium | 3 | 4 | Not Started |
| 7.6 | KAN-141 | Alert list | Hector Dessaux | High | 3 | 3 | Not Started |
| 7.7 | KAN-166 | Alert detail | Hector Dessaux | Medium | 2 | 5 | Not Started |
| 7.8 | KAN-139 | Day × hour heatmap | Linnéa Lindell | Medium | 2 | 3 | Not Started |
| 7.9 | KAN-155 | Savings report | Linnéa Lindell | High | 2 | 4 | Not Started |
| 7.10 | KAN-167 | Demo mode with historical data | Viktor Kalinowski | Medium | 2 | 5 | Not Started |
| 7.11 | KAN-161 | Mark alert as handled or false alarm | Raffaele Simo | Low | 2 | 5 | Not Started |
| 7.12 | KAN-168 | Export report | Linnéa Lindell | Low | 2 | 5 | Not Started |
| 7.13a | KAN-151 | Usability test script and testers | Inge Liv Haan | Medium | 1 | 4 | Not Started |
| 7.13b | KAN-158 | Usability test | Inge Liv Haan | Medium | 2 | 5 | Not Started |
| 7.14 | KAN-154 | Warnings in the dashboard | Viktor Kalinowski | High | 3 | 4 | Not Started |
| 7.15 | KAN-119 | First chart: hourly consumption per zone | Linnéa Lindell | High | 2 | 1 | Not Started |
| 7.16 | KAN-25 | Dashboard data layer | Viktor Kalinowski | High | 1 | 2 | Not Started |
| 7.17 | KAN-140 | Shared zone and date filters | Linnéa Lindell | Medium | 1 | 3 | Not Started |
| 8. Documentation, deployment & delivery · KAN-115 · docs, deployment plan, final presentation and final upload |  |  |  |  |  |  |  |
| 8.1a | KAN-27 | Docs site live: setup and data | Jo Elb | High | 2 | 2 | Not Started |
| 8.1b | KAN-142 | Docs: pipeline, model and detection rules | Jo Elb | High | 2 | 3 | Not Started |
| 8.1c | KAN-147 | Docs: validation results and limitations | Raffaele Simo | Medium | 1 | 4 | Not Started |
| 8.1d | KAN-169 | Docs complete | Jo Elb | High | 1 | 5 | Not Started |
| 8.2 | KAN-164 | User guide | Gabriele Grazzini | Medium | 1 | 5 | Not Started |
| 8.3 | KAN-159 | Deployment plan | Amélie Buysse | High | 2 | 5 | Not Started |
| 8.4 | KAN-29 | Final presentation and demo script | Jo Elb | High | 3 | 4 | Not Started |
| 8.5 | KAN-165 | Demo video | Gabriele Grazzini | Medium | 1 | 5 | Not Started |
| 8.6 | KAN-30 | Final upload | Jo Elb | High | 1 | 5 | Not Started |

Sprint overview

Story points and priorities per sprint, taken from the same Jira stories. The recurring Scrum-events item (KAN-28) runs in every sprint and is not counted here.

| Sprint | Dates | Stories | Story points | High | Medium | Low | Complete |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Sep 28 – Oct 11 | 13 | 22 | 12 | 1 | 0 | 2 |
| 2 | Oct 12 – 25 | 17 | 33 | 14 | 3 | 0 | 0 |
| 3 | Oct 26 – Nov 8 | 17 | 33 | 10 | 7 | 0 | 0 |
| 4 | Nov 9 – 22 | 16 | 33 | 9 | 7 | 0 | 0 |
| 5 | Nov 30 – Dec 14 | 13 | 22 | 3 | 7 | 3 | 0 |
| Total |  | 76 | 143 | 48 | 25 | 3 | 2 |